Dev Priority Backlog

Implementation Priorities & Timeline

2026.03.24 | Product → Dev Team | CEO Directed

| Total Items | 7 active items + 5 completed |
| --- | --- |
| Total Estimate | 23–28 dev days (~6 weeks) |
| P0 Items | 3 items (11–14 days) |
| P1 Items | 3 items (9–11 days) |
| P2 Items | 1 item (2–3 days) |

# 1. Completed Items

These items have already been shipped and are in production.

| Item | Category | Description | Effort |
| --- | --- | --- | --- |
| ✅ Indigo/Violet Color System | Design System | Global theme migration from blue to indigo/violet | 3d |
| ✅ Virtual Scrolling + Cmd+K + Focus Mode + Bulk Actions | UX Infra | Performance & power-user features for test case list | 5d |
| ✅ Logo Centering + Header Spacing | UI Polish | Sidebar logo alignment, header vertical spacing fix | 0.5d |
| ✅ 6-Tier Pricing Code | Billing | Free/Starter/Pro/Ent S/M/L pricing reflected in code | 2d |
| ✅ Sparse State Sprint 1 | Project List | EmptyState + SparseState + ProjectHeroCard components, layout branching | 3d |

Total completed: ~13.5 dev days

# 2. Priority Overview

All remaining items ranked by priority. P0 = must ship this quarter, P1 = should ship this quarter, P2 = nice to have.

| ID | Item | Priority | Estimate | Status | Blocked? |
| --- | --- | --- | --- | --- | --- |
| P0-1 | Discovery Logs Renaming (Sprint 4 Remaining) | P0 | 1 day | Not Started | No |
| P0-2 | Project Dashboard (07 Design – 7 Widgets) | P0 | 5–7 days | Not Started | No |
| P0-3 | Homepage Redesign (09 Design) | P0 | 5–6 days | Not Started | YES |
| P1-1 | Project List Enhancement (06 Design – Health Badge + Timeline) | P1 | 3–4 days | Not Started | No |
| P1-2 | Sparse State Sprint 2 (Sample Project + Invite + Import) | P1 | 3 days | Not Started | No |
| P1-3 | Onboarding Flow Improvement | P1 | 3–4 days | Not Started | No |
| P2-1 | Sparse State Sprint 3 (Animation + A/B Testing) | P2 | 2–3 days | Not Started | No |

CRITICAL PATH P0-1 (Rename, 1d) → P0-2 (Dashboard, 5–7d) → P0-3 (Homepage, 5–6d, blocked on Desi). P0-1 and P0-2 can run in parallel. P0-3 depends on Desi's revised design delivery.

# 3. Detailed Item Specifications

## P0-1: Discovery Logs Renaming (Sprint 4 Remaining)

| Priority | P0 – CRITICAL | Estimate | 1 day | Source: CEO directive, Sprint 4 carryover |
| --- | --- | --- | --- | --- |

Complete the Exploratory Sessions → Discovery Logs rename across all code, UI text, i18n keys, and navigation. Sprint 4 left some references unfinished.

### Tasks

- Rename in sidebar navigation (Exploratory Sessions → Discovery Logs)

- Update all i18n keys (en + ko) referencing exploratory/sessions

- Update page.tsx homepage content (features, FAQ)

- Update Supabase table/column names if applicable

- Search & replace across entire codebase for residual 'exploratory' references

- Verify no broken routes or dead links

Dependencies: None — can start immediately

Risk: Low. Renaming only, no logic changes.

## P0-2: Project Dashboard (07 Design – 7 Widgets)

| Priority | P0 – CRITICAL | Estimate | 5–7 days | Source: 07-project-dashboard design, CEO approved |
| --- | --- | --- | --- | --- |

Implement the project overview dashboard with 7 widgets as specified in the 07 design mockup. This is the primary view after clicking into a project.

### Tasks

- Widget 1: Project Health Score (circular progress + status)

- Widget 2: Test Coverage Overview (cases by status breakdown)

- Widget 3: Recent Test Runs (last 5 runs with pass/fail ratio)

- Widget 4: Milestone Progress (active milestones with timeline)

- Widget 5: Team Activity Feed (recent actions log)

- Widget 6: Quick Stats Cards (total cases, runs, members, pass rate)

- Widget 7: Upcoming Deadlines (milestone due dates)

- Responsive grid layout (2-col on desktop, 1-col on mobile)

- Data fetching via existing Supabase queries

- Loading skeletons for each widget

Dependencies: Requires existing project data model (available)

Risk: Medium. Multiple widgets = many integration points. Suggest building widget-by-widget.

## P0-3: Homepage Redesign (09 Design)

| Priority | P0 – CRITICAL | Estimate | 5–6 days | Source: 09-homepage-full design + CEO content map feedback |
| --- | --- | --- | --- | --- |

Implement the redesigned homepage based on 09 design while ensuring ALL 12 sections from the current page.tsx are preserved. Desi is revising the design to incorporate missing sections.

### Tasks

- Merge 09 design features (Keyboard Showcase etc.) with 9 Core Features

- Restore missing sections: How It Works, Integrations, Why Testably, FAQ

- Apply 'Exploratory Sessions' → 'Discovery Logs' in all homepage text

- Hero section: product screenshot placeholder (actual screenshot TBD)

- Footer cleanup: remove Blog, Community, Status, Careers links

- Update pricing section to match latest 6-tier spec

- Preserve FAQ structured data (SEO schema)

- Test EN/KO bilingual rendering for all sections

- Responsive breakpoints for all new layouts

Dependencies: Blocked: Waiting for Desi's revised 09 design with all sections included

Risk: High. Large page (1,300+ lines), bilingual, SEO-sensitive. Coordinate closely with Desi.

## P1-1: Project List Enhancement (06 Design – Health Badge + Timeline)

| Priority | P1 – HIGH | Estimate | 3–4 days | Source: 06-project-list-enhanced design |
| --- | --- | --- | --- | --- |

Enhance the 3+ projects list/grid view with health badges, activity timeline, and richer project cards as specified in the 06 design.

### Tasks

- Health badge component: Green/Yellow/Red based on recent pass rate

- Activity timeline: last 3 activities per project (inline, compact)

- Enhanced project card: add health badge, last activity, member avatars

- List view enhancements: health indicator column

- Sorting: add sort-by-health option

- Badge calculation logic: pass rate thresholds (>80% green, >50% yellow, red)

Dependencies: Existing project card in ProjectsContent.tsx (3+ state)

Risk: Low-Medium. Additive changes to existing components.

## P1-2: Sparse State Sprint 2 (Sample Project + Invite + Import)

| Priority | P1 – HIGH | Estimate | 3 days | Source: Dev_Handoff_Sparse_State.docx Sprint 2 spec |
| --- | --- | --- | --- | --- |

Add engagement features to the sparse state: template-based sample project creation, team invite flow from empty state, and project import capability.

### Tasks

- TemplateCards component with 4 templates (QA Testing, API Testing, Sprint QA, Mobile)

- CreateProjectModal: template pre-fill support (name, description, default cases)

- GettingStartedChecklist component (5-item checklist with auto-completion)

- Checklist persistence (localStorage) and dismissal logic

- Invite team CTA in side panel (links to existing invite modal)

Dependencies: Sprint 1 complete (EmptyState + SparseState already merged)

Risk: Low. Well-defined spec in Dev_Handoff_Sparse_State.docx.

## P1-3: Onboarding Flow Improvement

| Priority | P1 – HIGH | Estimate | 3–4 days | Source: CEO directive, product roadmap |
| --- | --- | --- | --- | --- |

Improve the post-signup experience: guided first-run flow, contextual tooltips, and progressive disclosure of features.

### Tasks

- First-run detection: track user's first login timestamp

- Welcome modal with 3-step intro (Create Project → Add Tests → Run)

- Contextual tooltips on first visit to each major feature

- Progress indicator: show onboarding completion in sidebar or header

- Connect to GettingStartedChecklist (from Sparse State Sprint 2)

- Auto-dismiss after 14 days or manual skip

Dependencies: Sparse State Sprint 2 (GettingStartedChecklist)

Risk: Medium. Touches multiple pages. Needs coordination with Sparse State work.

## P2-1: Sparse State Sprint 3 (Animation + A/B Testing)

| Priority | P2 – MEDIUM | Estimate | 2–3 days | Source: Dev_Handoff_Sparse_State.docx Sprint 3 spec |
| --- | --- | --- | --- | --- |

Polish the sparse state with smooth layout transitions and set up A/B testing framework for empty state variants.

### Tasks

- Framer Motion: layout transitions between 0→1→2→3+ states

- Card entrance animations (fade-up on create)

- Analytics events: view, click, conversion tracking

- A/B test framework: variant assignment + event logging

- Responsive breakpoints for mobile/tablet sparse states

- E2E tests for all sparse state transitions

Dependencies: Sprint 1+2 complete

Risk: Low. Polish work, not blocking any other features.

# 4. Suggested 6-Week Timeline

Assumes 1 full-stack developer. Can be accelerated with parallel work if 2 developers available.

| Week | Work Items | Days | Milestone |
| --- | --- | --- | --- |
| Week 1 | P0-1: Discovery Logs rename (1d) P0-2: Dashboard widgets 1–4 (4d) | 5d | Dashboard scaffolding + rename done |
| Week 2 | P0-2: Dashboard widgets 5–7 + polish (3d) P1-1: Project List 06 enhancements (2d) | 5d | Dashboard complete, list upgrades started |
| Week 3 | P1-1: Project List finish (2d) P1-2: Sparse State Sprint 2 (3d) | 5d | 06 list done, templates + checklist |
| Week 4 | P0-3: Homepage redesign (5d) | 5d | Full homepage implementation (if Desi design ready) |
| Week 5 | P0-3: Homepage polish + testing (1d) P1-3: Onboarding flow (4d) | 5d | Homepage shipped, onboarding started |
| Week 6 | P1-3: Onboarding finish (1d) P2-1: Sparse Sprint 3 animations (2d) Buffer (2d) | 5d | All items complete + buffer |

BLOCKER ALERT P0-3 (Homepage Redesign) is blocked on Desi's revised 09 design. If design delivery is delayed, swap Week 4 work with P1-3 (Onboarding) to keep momentum. Notify PM if this happens.

## 5. Parallelization Opportunities (2-Dev Scenario)

If a second developer is available, the timeline can be compressed to ~4 weeks:

| Week | Dev A | Dev B |
| --- | --- | --- |
| 1–2 | P0-2: Dashboard (7 widgets) | P0-1: Rename (1d) + P1-1: List Enhancement (3d) |
| 2–3 | P0-3: Homepage (if design ready) | P1-2: Sparse Sprint 2 + P1-3: Onboarding |
| 4 | P0-3: Homepage finish + P2-1: Animations | Testing + bug fixes + buffer |

# 6. Executive Summary

| Priority | Items | Days | Weeks | Key Deliverable |
| --- | --- | --- | --- | --- |
| P0 CRITICAL | 3 | 11–14d | ~3 wks | Dashboard + Homepage + Rename |
| P1 HIGH | 3 | 9–11d | ~2 wks | List upgrade + Templates + Onboarding |
| P2 MEDIUM | 1 | 2–3d | <1 wk | Animations + A/B testing |
| TOTAL | 7 | 23–28d | ~6 wks | Full Q2 delivery |

RECOMMENDATION Start P0-1 (Rename) and P0-2 (Dashboard) simultaneously on Day 1. Rename is a quick 1-day win that clears tech debt. Dashboard is the highest-value deliverable for users. Homepage depends on Desi's design revision — keep it in Week 4 slot and swap with P1 items if design is delayed.